## Sheet1
Risk ID | Description | Category | Probability | Impact | Mitigation Plan | Owner | Status
R001 | Schedule delays due to resource shortage | Schedule | High | High | Assign backup testers | QA Manager | Open
R002 | API integration issues with third-party system | Technical | Medium | High | Use mock APIs for early testing | Dev Lead | Open
R003 | Incomplete requirements documentation | Process | Medium | Medium | Organize BA review meetings | Product Owner | Mitigated
R004 | Test environment downtime | Infrastructure | Low | High | Add cloud backup environment | IT Admin | Open